## feature
feature | sub-features | database | status | date | tech | remark
load data | show data in the table |  | done | May
| add photo |  | done | 2020-06-01 |  | /ebook/images/
| show data in multipages |  | done | 2020-06-02
search | search book title | book | done | May | ajax JS java
| view search results by different criteria |  | open | 2020-06-04
| grid or list view |  | done | 2020-06-03
account | login | user | done | May
| sign up | user | done | May
| logout | user | done |  |  | session invalidate
cart | add to cart |  | done | May
| update |  | done | May
| remove |  | done | May
checkout | contact info | contact | done | May
| credit info |  | done | May
May
order | placeorder | order | issue ,can not populate order data into db | May
view order
invoice |  | invoice | done | May
admin | login | admin | done | 2020-05-31 | authentication
| insert book |  | done | 2020-06-01
| update book |  | done | 2020-06-01
| delete book |  | open
view user
| search book by criteira |  | open
| search order |  | open
| process invoice |  | open
open
email |  |  | open
open
post |  |  | open
open
review |  |  | open
| import js |  |  | 2020-06-03

## issues
CANNOT USE module in script.
cannot inser order to database order table